## Sheet1
S.No	Date	Activities	Status
1	12/09/16	Gitlab Study and / Gitlab installation.	Completed
2	13/09/16	Gitlab configuration and gitlab document prepared	Completed
3	14/09/16	LDAP Study and intregation	Completed
4	16/09/16	LDAP intregation and / User creation issues,vms_va build work	Pending / User authentication
5	19/09/16	BEL_VMS project full backup is restored in gitlab / SMTP server install and configured in ubuntu server	Completed
6	20/09/16	Jenkins installed and configured in ubuntu and creating / Windows slave .Prepared jenkins document	Completed
7	21/09/16	windows and ubuntu is installation and configuration of the following. / - Jdk / - Git / - Cmake / - Maven / gitlab command document prepared	Completed
8	22/09/16	The following components are build / - Management server / - Streaming server / - Desktop client / - Management client / Web UI on win slave	Completed
9	23/09/16	Sonarqueb study / Sonarqueb installation and configuaration on windows.	Some configuration / Issues.
10	25/09/16	Klockwork study / Apache tomcat server document prepared	In progress
11	26/09/16
12